## Sheet1
Event Name | Task/Phase | Start | End | Include | Status
CES 2024 | Prep | 2026-01-02 | 2026-01-06 | Yes | Complete
CES 2024 | Shipping In | 2026-01-07 | 2026-01-10 | Yes | Complete
CES 2024 | Main Event | 2026-01-11 | 2026-01-14 | Yes | Complete
CES 2024 | Shipping Out | 2026-01-15 | 2026-01-18 | Yes | Complete
MWC Barcelona | Prep | 2026-02-18 | 2026-02-22 | Yes | Complete
MWC Barcelona | Shipping In | 2026-02-23 | 2026-02-26 | Yes | Delayed
MWC Barcelona | Main Event | 2026-02-27 | 2026-03-02 | Yes | At Risk
MWC Barcelona | Shipping Out | 2026-03-03 | 2026-03-06 | Yes | On Track
NAB Show | Prep | 2026-04-05 | 2026-04-10 | Yes | On Track
NAB Show | Shipping In | 2026-04-11 | 2026-04-13 | Yes | On Track
NAB Show | Main Event | 2026-04-14 | 2026-04-17 | Yes | On Track